## Dahboard
Period | 2020-21
Program Name | STEM from Home Web Portal
Beneficiaries | Grade 5 to Grade 10 Students

## Gantt Chart
| Planned |  |  | Actual
Task (User Input) | Start Date (User Input) | End Date | Duration (User Input) | Start Date (User Input) | End Date (User Input) | Duration | Task Status (User Input) | time axis 2020-07-20 to 2021-01-17
Project Initiation | 2020-07-20 | 2020-07-21 | 1 | 2020-07-20 | 2020-07-21 | 2 | Completed | bar: 2020-07-20 to 2020-07-21
[8 empty] | A | A
Review of RFP v2.0 | 2020-07-21 | 2020-07-31 | 8 | 2020-07-21 |  | -31452 | In Progress | bar: 2020-07-21 to 2020-07-31
Releaseof RFP | 2020-08-03 | 2020-08-04 | 1 |  |  | #REF! | In Progress | bar: 2020-08-03 to 2020-08-04
Accept Proposals from Vendor | 2020-08-03 | 2020-08-08 | 5 |  |  | #REF! | In Progress | bar: 2020-08-03 to 2020-08-08
Procurement Process | 2020-08-10 | 2020-08-17 | 5 |  |  | #REF! | In Progress | bar: 2020-08-10 to 2020-08-17
Raise PO | 2020-08-19 | 2020-08-21 | 2 |  |  | #REF! | In Progress | bar: 2020-08-19 to 2020-08-21
Web Portal Readiness | 2020-07-21 | 2020-08-03 | 10 |  |  | #REF! | In Progress | bar: 2020-07-21 to 2020-08-03
Activity 1 | 2020-07-21 | 2020-07-25 | 4 |  |  | #REF! | In Progress | bar: 2020-07-21 to 2020-07-25
Activity 2 | 2020-07-25 | 2020-07-31 | 4 |  |  | #REF! | In Progress | bar: 2020-07-25 to 2020-07-31
Activity 3 | 2020-08-03 | 2020-08-07 | 4 |  |  | #REF! | In Progress | bar: 2020-08-03 to 2020-08-07
Activity 4 | 2020-08-08 | 2020-08-13 | 4 |  |  | #REF! | In Progress | bar: 2020-08-08 to 2020-08-13
Activity 5 | 2020-08-14 | 2020-08-20 | 4 |  |  | #REF! | In Progress | bar: 2020-08-14 to 2020-08-20
Activity 6 | 2020-08-21 | 2020-08-26 | 4 |  |  | #REF! | In Progress | bar: 2020-08-21 to 2020-08-26
Activity 7 | 2020-08-27 | 2020-09-01 | 4 |  |  | #REF! | In Progress | bar: 2020-08-27 to 2020-09-01
Activity 8 | 2020-09-02 | 2020-09-07 | 4 |  |  | #REF! | In Progress | bar: 2020-09-02 to 2020-09-07
Activity 9 | 2020-09-08 | 2020-09-12 | 4 |  |  |  | In Progress | bar: 2020-09-08 to 2020-09-12
Activity 10 | 2020-09-13 | 2020-09-17 | 4 |  |  |  | In Progress | bar: 2020-09-13 to 2020-09-17
Activity 11 | 2020-09-18 | 2020-09-23 | 4 |  |  |  | In Progress | bar: 2020-09-18 to 2020-09-23
Activity 12 | 2020-09-24 | 2020-09-29 | 4 |  |  |  | In Progress | bar: 2020-09-24 to 2020-09-29
Activity 13 | 2020-09-30 | 2020-10-06 | 4 |  |  |  | In Progress | bar: 2020-09-30 to 2020-10-06
Activity 14 | 2020-10-07 | 2020-10-12 | 4 |  |  |  | In Progress | bar: 2020-10-07 to 2020-10-12
Activity 15 | 2020-10-13 | 2020-10-17 | 4 |  |  |  | In Progress | bar: 2020-10-13 to 2020-10-17
Web Portal Milestone 1 |  | 0 |  |  |  |  | In Progress
Web Portal Milestone 2 |  | 0 |  |  |  |  | In Progress
Web Portal Milestone 3 |  | -1 |  |  |  |  | In Progress
Web Portal Milestone 4 |  | -1 |  |  |  |  | In Progress
Web Portal Milestone 5 |  | -1 |  |  |  |  | In Progress
Web Portal Milestone 6 |  | -1 |  |  |  |  | In Progress
Web Portal Launch | 2020-09-10 | 2020-10-04 | 20 |  |  |  | In Progress | bar: 2020-09-10 to 2020-10-04
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
|  | -1 |  |  |  |  | In Progress
-1
2. Completed Timeline Breakup
Delayed
Actual
Extended
1. Overall Task Status
Pending
In Progress
Completed

## Web Hosting Services Budget
Vendor | Godaddy | Bluehost | Dreamhost | Hostinger
Pricing | Rs. 99 - Starter | Rs. 199 - Basic | $4.95 - Starter | Rs. 59 - Single
| Rs.199 - Economy | Rs. 299 - Plus | $10.95 - Unlimited | Rs. 119 - Premium
| Rs. 299 - Deluxe | Rs. 299 - Choice Plus |  | Rs.219 - Business
| Rs. 499 - Ultimate | Rs. 859 - Pro
Website Domain | One - Starter | One - Basic | One - Starter | One - Single
| One - Economy | Unlimited - Plus | Unlimited - Unlimited | Unlimited - Premium
| Unlimited - Deluxe | Unlimited - Choice Plus |  | Unlimited- Business
| Unlimited - Ultimate | Unlimited - Pro
Storage | 30GB - Starter | 50 GB SSD - Basic | Fast SSD storage for both
| 100 GB - Economy | Unlimited - Plus
| Unlimited - Deluxe | Unlimited - Choice Plus
| Unlimited - Ultimate | Unlimited - Pro
Database | One - Starter |  |  | One MySQL - Single
| 10 - Economy |  |  | Unlimited MySQL - Premium
| 25 - Deluxe |  |  | Unlimited MySQL - Business
Unlimited - Ultimate
Professional Email | Free - Economy | 30 Days of Microsoft email included for all except Basic | Email $1.67 - Starter
| Free - Deluxe |  | Unlimited Email - Unlimited
Free - Ultimate
1-year trail for all packages
SSL Certificate | 1-year - Ultimate | Free for all | Free for all
Github Integration |  |  |  | Supported for all

## Program Budget
Program Budget
Sr No | Budget Head | Column1
1 | Purchase of Domain Name
2 | Purchase of Web Hosting Services
3 | Purchase of Data Server
4 | Purchase of Video Service Provider Premium Account
5 | Web Portal Development
6 | Annual Maintenance
7 | Content Development Cost
8 | Graphic Design Cost
9 | Legal Consultation Cost

## Holidays (hidden)
# Please add holidays dates to exclude days from project ending date calculation.
Date | Day | Holiday
2020-07-30 | Friday | ID-UL-JUHA
2020-08-15 | Saturday | Independence day
2020-10-02 | Friday | Gandhi jayanti
2020-10-26 | Monday | Vijayadashmi
2020-10-29 | Thursday | Maulad Nabi
2020-11-14 | Saturday | Diwali
2020-12-25 | Friday | Christmas Day
2021-01-15 | Friday | Makar Sankaranti